## c programming - case
C Programming - Case Study
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
File Handling
Name | Assigned To | Status | Due date | Notes
First Meeting |  | Done | 2024-06-04
Flowchart | John Mathew Parocha, Aya Del Rosario | Done | 2024-06-14
Main Menu : Registration, Login, Admin |  | Done | 2024-06-05
Transaction Process (Snippet) | Marie Purawan, Summer Parativo, John Mathew Parocha, Corish Anne Arce, Aya Del Rosario | Done | 2024-06-07 | For Everyone
Prototype v1 |  | Done | 2024-06-08
QA System Tester (First Phase) |  | Working on it
Second Meeting |  | Working on it
Main Menu Design Revision | Corish Anne Arce | Done | 2024-06-10
Admin Dashboard Design Revision | Summer Parativo | Done | 2024-06-10
User Dashboard Design Revision |  | Working on it
Transaction Menu Design Revision |  | Working on it
QA System Tester (Second Phase) |  | Not Started
Final Revision |  | Not Started
Documentation | Aya Del Rosario | Working on it | 2024-06-14
Final Output |  | Not Started | 2024-06-15
2024-06-04 to 2024-06-15
Linked List
Name | Assigned To | Status | Due date | Notes
Create a Linear Linked List | Marie Purawan | Done | 2024-06-17
Display a Linear Linked List | Marie Purawan | Done | 2024-06-18
Insert a number in the Linear Linked List | Corish Anne Arce | Done | 2024-06-19
Delete a number from the Linear Linked List | Summer Parativo | Done | 2024-06-20
Search a number | Summer Parativo | Done | 2024-06-21
v1 |  | Done | 2024-06-22
2024-06-17 to 2024-06-22